## status
GOVERNMENT OF SINDH CULTURE, TOURISM & ANTIQUITIES DEPARTMENT MONTHLY PROGRESS REPORT FOR THE MONTH OF Nov 2019 DEVELOPMENT SCHEMES
(Rs. In million)
No. of Scheme |  | Allocation 2019-20 |  |  | Released Fund upto NOV, 2019 |  |  | Expenditure upto Nov, 2019
|  | Cap: | Rev: | Total | Cap: | Rev: | Total | Cap: | Rev: | Total | JULY | 3.7507 | 1.1834
On-Going | 23 | 1418.363 | 230.85 | 1649.213 | 1029.248 | 73.145 | 1102.393 | 659.411 | 12.377 | 671.788 | AUG | 25.735 | 0.84501
New | 23 | 237.847 | 53.19 | 291.037 | 0 | 0 | 0 | 0 | 0 | 0 | SEP | 50.41
Total | 46 | 1656.21 | 284.04 | 1940.25 | 1029.248 | 73.145 | 1102.393 | 659.411 | 12.377 | 671.788 | OCT | 78.934 | 40.456
[11 empty] | NOV | 393.526 | 0.591
1.685
[9 empty] | 9.739 |  |  |  | 13.489
[9 empty] | 0.238 |  |  | 552.3557 | 2.826
[9 empty] | 0.714 |  |  |  | 2.634
[9 empty] | 0.753 |  |  |  | 8.963
[9 empty] | 11.444 |  |  |  | 70.644

## 73.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.73.
2 | NAME OF PROJECT | Sindh indigenious Traditional Crafts Company (SITCO) (Capacity Building & Assistance to Producer / Civil Society Organization)
3 | LOCATION (TALUKA/DISTRICT): | Karachi
4 | FINANCIAL STATUS:
|  | Cap: | Rev: | Total:
| i) ADP Allocations for the current Year | 0 | 10 | 10
| ii) Total Release for the Current Year | 0 | 0 | 0
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 0 | 514 | 514
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
| 0 | 0 | 0 | 0
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 74.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.74.
2 | NAME OF PROJECT | Protection, Preservation and Promotion of Protected Archaeological Sites and Monuments in Sindh (Revised) (C:836.198+R:154.802) (SDG # 8,11)
3 | LOCATION (TALUKA/DISTRICT): | Sindh | [5 empty] | 299.178
4 | FINANCIAL STATUS: | Cap: | Rev: | Total:
477.801
| i) ADP Allocations for the current Year | 600.604 | 80.912 | 681.516
| ii) Total Release for the Current Year | 600.604 | 40.456 | 641.06
| iii) Expenditure during the month | 98.792 | 16.258 | 115.05
| iv) Total Expenditure since commecement | 724.467 | 91.29 | 815.757 | 0.13637 | 233.489 | 631.459
5 | PHYSICAL STATUS |  |  |  | 576.394
| Physical achievements during the month under report |  |  |  | 98.792
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS | 477.602
| Capital | -- |  | - | 147.873
1 | Country brick masonry | P.Cft | 202498.582 |  | 625.475
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 75.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.75
2 | NAME OF PROJECT | Development of Summer Resorts at Gorakh Hills District Dadu (Re-revised) (C:2814.000+R:232.000) (SDG # 8)
3 | LOCATION (TALUKA/DISTRICT): | Dadu
4 | FINANCIAL STATUS: | C: | Rev: | Total:
| i) ADP Allocations for the current Year | 245 | 5 | 250
| ii) Total Release for the Current Year | 0 | 0 | 0
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 2022.463 | 147.135 | 2169.598
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
| 0 | 0 | 0 | 0
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 76.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.76
2 | NAME OF PROJECT | Establishment of Motels, Improvement / Renovation of existing Motels / Resorts in Sindh Sehwan, Thatta including Umerkot. (Revised) (i)
3 | LOCATION (TALUKA/DISTRICT): | Jamshoro, Thatta & Umerkot |  |  |  | 14.98
4 | FINANCIAL STATUS | Cap: | Rev: | Total:
| i) ADP Allocations for the current Year | 58.978 | 10 | 68.978
| ii) Total Release for the Current Year | 58.979 | 0 | 58.979 | 14.7445
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 87.046 | 2.948 | 89.994
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
1 | Civil | 0
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 77.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.77
2 | NAME OF PROJECT | Conservation / Restoration / Preservation of Retaining wall and Dangerous Structures of Pucca Fort Hyderabad. (Revised)
3 | LOCATION (TALUKA/DISTRICT): | Hyderabad
4 | FINANCIAL STATUS | Cap: | Rev: | Total:
| i) ADP Allocations for the current Year | 30 | 0 | 30
| ii) Total Release for the Current Year | 30 | 0 | 30
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 142.892 | 14.217 | 157.109 | 125.666
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
PUCCA FORT MUSEUM
CONSERVATION OF MUSEUM
1 | Dismentling of badly damaged and cracked brick masonary walls | CFT | 10673
| Revenue | -- | 0
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 78.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.78.
2 | NAME OF PROJECT | Preservation of Old Chief Court Session Court Khairpur (Revised) (C:139.979+R:14.311) (SDG # 11)
3 | LOCATION (TALUKA/DISTRICT): | Khairpur
4 | FINANCIAL STATUS: | Cap: | Rev: | Total:
| i) ADP Allocations for the current Year | 93.298 | 1.183 | 94.481
| ii) Total Release for the Current Year | 93.298 | 0.591 | 93.889
| iii) Expenditure during the month | 0 | 0.3265 | 0.3265
| iv) Total Expenditure since commecement | 92.248 | 13.3325 | 105.5805 | 13.124
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
| - | 0 | 0 | 0
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 79.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.79
2 | NAME OF PROJECT | Construction of Museum, Library & Allied Facilities at Dargah Sharif Hazrat Allama Mian Ghulam Muhammad Mahesar, Kamal Dero at Taluka Gambat (Revised) (C:94.357+R:3.370) (SDG # 4)
3 | LOCATION (TALUKA/DISTRICT): | Khairpur
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 40.051 | 3.37 | 43.421
| ii) Total Release for the Current Year | 20.0255 | 1.685 | 21.7105
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 56.297 | 0 | 56.297
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
| 0 | 0 | 0 | 0
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 80.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.80
2 | NAME OF PROJECT | Conservation / Rehabilitation of Mitha Ram Hostel, Karachi (C:47.231+R:39.645) (SDG # 11)
3 | LOCATION (TALUKA/DISTRICT): | Karachi
4 | FINANCIAL STATUS:(U/R)
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 1 | 0 | 1
| ii) Total Release for the Current Year | 0.25 | 0 | 0.25
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 47.137 | 0 | 47.137
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
| 0 | 0 | 0 | 0
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 81.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.81
2 | NAME OF PROJECT | Restoration and Conservation of Kot Diji Fort District Khairpur (C:147.060+R:0.000)
3 | LOCATION (TALUKA/DISTRICT): | Khairpur
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 21.277 | 0 | 21.277
| ii) Total Release for the Current Year | 21.277 | 0 | 21.277 | 100
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 136.219 | 0 | 136.219
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
1 | Preparing of detailed topographical survey plan | P.JOB | 1 | 0
2 | Terrace flooring 3" | P.SFT | 20716
3 | Dusting and cleaninf of wall | P.SFT | 85013.63
4 | Restoration of wall by burnt brick | P.CFT | 2473.08
OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 82.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.82
2 | NAME OF PROJECT | Construction of Auditorium Hall, Rest House and Main Entrance Gate at Dargah Hazrat Sardar Ahmed Shah Lakyari Taluka Saeedabad, District Matiari. (C:73.021+R:26.979) (SDG # 4)
3 | LOCATION (TALUKA/DISTRICT): | Matiari
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 15.723 | 26.979 | 42.702
| ii) Total Release for the Current Year | 15.723 | 13.489 | 29.212
| iii) Expenditure during the month | 7.615 | 0.05 | 7.665
| iv) Total Expenditure since commecement | 64.57 | 0.05 | 64.62
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
| Tiles glazed 6" x 6" | %SFT | 675.717 | 0
| Priming Coat of chalk distemper | %SFT | 6212.78
| Distemering Three coats | %SFT | 6212.78
| White marble Flooring fine | SFT | 8526.23
| Burma teak wood doors windows | P.SFT | 520.06
| Thick marble Slab | P.SFT | 80.062
| RCC work | P.Cft | 2131.89
| Fabrication of tor steel | Per.Cwt | 87.233
| Wiring for light or fan point | Per point | 133
| wiring for plug point | Per point | 64
| Wiring for call bell point | Per point | 4
| PVC insulated with size 2-7/.029 | Per Meter | 480
| PVC insulated with size 2-7/.036 | Per Meter | 137
| PVC insulated with size 2-7/.044 | Per Meter | 130
| PVC insulated with size 4-7/.044 | Per Meter | 163
| Circuit breaker 6,10,15,20,30,40,50, & 63 amp | Per No. | 20
| Circuit breaker 3,5,10,15,20, & 30 amp | Per No. | 11
| Circuit breaker 15,20,30,40,50, & 60 amp | Per No. | 14
| One way SP 10/15 amp | Per No. | 107
| Two pin 5 amp | Per No. | 13
| Three pin 5 amp | Per No. | 12
| Three pin 10/15 amp | Per No. | 15
| Bakelite ceiling rose | Per No. | 18
| Circuit breaker 400 | Per No. | 1
| Distibution board 16 SWG | Each | 1
| Wall bracket fan | Per No. | 14
| Energy saver | Per No. | 60
| 2-40 volts tube light | Per No. | 8
| 4-40 volts tube light | Per No. | 14
| Exaust fan | Per No. | 9
| Brass ceiling fan | Per No. | 22
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 83.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.83
2 | NAME OF PROJECT | Establishment of Auditorium at Dadu (C:42.208+R:24.830) (Revised) (SDG # 4)
3 | LOCATION (TALUKA/DISTRICT): | Dadu
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 25.038 | 22.168 | 47.206
| ii) Total Release for the Current Year | 12.519 | 0 | 12.519 | 25.036
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 29.684 | 2.662 | 32.346
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
| 0 | 0 | 0 | 0
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 84.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.84
2 | NAME OF PROJECT | Provision of Ferry Service at Sukkur and Keenjhar Lake to facilitate the Tourists. (Revised) (C:92.529+R:7.039) (SDG # 8)
3 | LOCATION (TALUKA/DISTRICT): | Sukkur & Thatta
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total: | 30.115
5.99
| i) ADP Allocations for the current Year | 60.337 | 0 | 60.337 | 24.125
| ii) Total Release for the Current Year | 60.337 | 0 | 60.337
| iii) Expenditure during the month | 5.99 | 0 | 5.99
| iv) Total Expenditure since commecement | 62.306 | 7.039 | 69.345 |  | 26.915
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
1 | Thick galaxy granite slab | P.SFT | 1414 | 0
2 | Development and construction of ferry | P.No | 3
3 | Development and construction of jetty | Each | 2
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 85.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.85
2 | NAME OF PROJECT | Provision of missing facilities at Kashi Institute @ Bhitshah & Conservation & Restoration of Dabgeer Mosque at Thatta. (Revised)
3 | LOCATION (TALUKA/DISTRICT): | Thatta & Matiari
4 | FINANCIAL STATUS
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 25.072 | 5 | 30.072
| ii) Total Release for the Current Year | 25.072 | 0 | 25.072
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 31.375 | 1.919 | 33.294 | 15.026
5 | PHYSICAL STATUS |  |  |  | 16.349
| Physical achievements during the month under report |  |  |  | 31.375
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
1 | Repair of domes holes | Each | 2 | 0
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 86.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.86
2 | NAME OF PROJECT | Establishment & Improvement of Samabra Inn Larkano (Revised) (C:72.845+R:12.155)
3 | LOCATION (TALUKA/DISTRICT): | Larkano
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 31.067 | 12.155 | 43.222
| ii) Total Release for the Current Year | 31.067 | 0 | 31.067
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 42.607 | 1.29 | 43.897
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
1 | Excavation | %0Cft | 12914.6
2 | Providing anti termite | P.Sft | 2224.127
3 | Cement concrete brick | %Cft | 31049.151
4 | paving blocks | P.Sft | 10000
5 | fabrication | Per.Cwt | 1412.376
6 | RCC work | P.Cft | 20258.691 | 0
7 | pacca brick | %Cft | 8361.62
8 | White marble | P.Sft | 1245.975
9 | Providing and fixing 3/8" thick marble | P.Sft | 5648.382
10 | Primary coat | %Sft | 15176
11 | Distempering | %Sft | 15176.02
12 | Two coats of bitumen | %Sft | 9158.08
13 | Providing and laying porecelene | P.Sft | 30.32
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 87.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.87
2 | NAME OF PROJECT | Establishment of Museum, Research Centre and Rest House @ Archaeological Site at Chanhyo Jo Daro (Modified)
3 | LOCATION (TALUKA/DISTRICT): | S.B.A
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 40.443 | 16 | 56.443
| ii) Total Release for the Current Year | 40.443 | 0 | 40.443
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 75.291 | 1.01 | 76.301
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
CIVILWORK
1 | Random rubble masonary | %CFT | 10704.55
2 | RCC work including all labour and material | P-CFT | 5507.89
3 | Fabrication of tor steel reinforcement for cement concrete | P-CWT | 341.44
4 | Cement concrete plain including placing compacting | %CFT | 951.99
5 | Two coats of bitumen laid | %SFT | 5919.99
6 | Cement concrete plain including placing compacting | %CFT | 4110.27
7 | Pacca brick work in foundation | %CFT | 5609
8 | Damp proof course with cement sand and shingle concrete | %SFT | 1650.12
9 | Filling watering and ramming | %0CFT | 41340
10 | Extra lead 2 miles | %CFT | 41340
11 | Angle iron vertical post for barbed wire fencing of size 2" x 2" 1/4" | P-RFT | 836
12 | Cement plaster 1:4 inside U/G tank
13 | Applying bitumen coating on RCC external surface of U.G. tank
CARTAGE OF MATERIAL
1 | Cement | P-BEG | 13891.29
2 | Fine aggregates sand | P-CFT | 46883.03
3 | Course Aggregates crush | P-CFT | 71634.27
4 | Steel | P-CWT | 150.08
5 | Bricks | CFT | 302757.12
6 | Stone | P-No | 13380.68
CIVILWORK
1 | RCC work including all labour and material | P-CFT | 2966
2 | Fabrication of tor steel reinforcement for cement concrete | P-CWT | 98.01
3 | Earth for slush or daldal | %0CFT | 1150
4 | Erection and removal of centering for RCC | %CFT | 5521.81
5 | Cemenr concrete plain including placing compacting | %CFT | 2025.12
6 | Filling watering and ramming | %0CFT | 19400.64
7 | Two coats of bitumen laid | %SFT | 7569.2
8 | Cemenr concrete plain including placing compacting | %CFT | 1516.22
DIFFERENCE IN COST OF MATERIAL
1 | Cement | Per bag | 15378.01
2 | Steel | Per ton | 150.08
| Bricks | per no | 302757.12
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 88.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.88
2 | NAME OF PROJECT | Missing Allied Facilities of Tourism Information Centre PITHM Karachi (C:23.420+R:6.580)
3 | LOCATION (TALUKA/DISTRICT): | Karachi
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 1 | 0 | 1
| ii) Total Release for the Current Year | 0.25 | 0 | 0.25
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 0 | 0 | 0
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
| 0 | 0 | 0 | 0
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 89.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.89
2 | NAME OF PROJECT | Missing Allied Facilities Motel at Hawksbay Karachi (C:32.650+R:7.350)
3 | LOCATION (TALUKA/DISTRICT): | Karachi
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 1 | 0 | 1
| ii) Total Release for the Current Year | 0.25 | 0 | 0.25
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 0 | 0 | 0
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
| 0 | 0 | 0 | 0
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 90.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.90
2 | NAME OF PROJECT | Missing Allied Facilities for Motel and Information Centre at Mohen-Jo-Daro, Larkano (C:23.196+R:6.814)
3 | LOCATION (TALUKA/DISTRICT): | Larkano
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 1 | 0 | 1
| ii) Total Release for the Current Year | 0.25 | 0 | 0.25
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 0 | 0.697 | 0.697
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
| 0 | 0 | 0 | 0
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 91.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.91
2 | NAME OF PROJECT | Establishment of Amjad Sabri Institute of Sufi Music and Qawali at Karachi (C:34.498+R:25.502)(SDG # 8)
3 | LOCATION (TALUKA/DISTRICT): | Karachi
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 1 | 0 | 1
| ii) Total Release for the Current Year | 0.25 | 0 | 0.25
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 0 | 1.061 | 1.061
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
| 0 | 0 | 0 | 0
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 92.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.92
2 | NAME OF PROJECT | Missing Allied facilities of Cultural Complex at Sukkur (C:62.938+R:7.062) (SDG # 8)
3 | LOCATION (TALUKA/DISTRICT): | Sukkur
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 27.46 | 5.652 | 33.112
| ii) Total Release for the Current Year | 27.46 | 2.826 | 30.286
| iii) Expenditure during the month | 9.718 | 1.186 | 10.904
| iv) Total Expenditure since commecement | 56.234 | 2.744 | 58.978
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
CIVIL WORK
1 | False cailing of plaster paris | %SFT | 6396.802
2 | Filling watering ramming earth under floor ezcavated from out side | CFt | 8518.75
3 | P/F cement paving blocks flooring | PSFT | 6393.996
4 | suppling and filling sand under floor | %CFT | 6394.13
5 | Add extra 3 miles lead | %CFT | 6394.13
6 | CCB or stone | %CFT | 2107
7 | Pacca brick work | %CFT | 267.6
8 | Cement plaster 1:4 upto 20' height 1/2" thick | %SFT | 713.61
9 | Cement plaster 1:4 upto 20' height 3/8" thick | %SFT | 713.61
10 | Excavation in foundation of building bridges | %0CFT | 1578.13
11 | CCB or stone ballast | %CFT | 473.44
12 | Pacca brick work | %CFT | 1075.27
13 | RCC work | P.CFT | 142.93
14 | Fabrication of mild steel reinforcement for CC | P.CWT | 11.36
15 | Wiring for light or fan | Per point | 500
16 | Wiring for plug point | Per point | 280
17 | Wiring for call bell point | Per point | 8
18 | PVC insulated with size 2-7/.029 | P-Mtr | 3200
19 | PVC insulated with size 2-7/.036 | P-Mtr | 1600
20 | PVC insulated with size 2-7/.044 | P-Mtr | 2200
21 | Two point 5 amp plug | Each | 90
22 | One way SP 5amp | Each | 66
23 | S/F LED light square | Each | 200
24 | P/F european type white glazed | Nos. | 4
25 | Squating type white glazed | Nos. | 16
26 | Lavatory basin in whilte glazed | Nos. | 14
27 | PVC floor trap | Nos. | 40
28 | Long bip cock | Nos. | 22
29 | Muslim shower | Nos. | 4
30 | Concealed stop cock | Nos. | 34
31 | Doubled bowl | Nos. | 2
32 | Bowl mixture | Nos. | 2
33 | Valinity | Nos. | 14
| PVC pressure pipe of class C | RFT | 100
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 93.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.93
2 | NAME OF PROJECT | Missing Allied facilities of Motel/Hotel at Garhi Khuda Bux Bhutto Larkano (C:63.693+R:6.307)
3 | LOCATION (TALUKA/DISTRICT): | Larkano
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 62.412 | 5.268 | 67.68
| ii) Total Release for the Current Year | 62.412 | 2.634 | 65.046
| iii) Expenditure during the month | 1.696 | 1.127 | 2.823
| iv) Total Expenditure since commecement | 25.21 | 2.077 | 27.287
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
1 | Excavation | %0Cft | 10351
2 | RCC work | P.Sft | 9770.72 | 0
3 | fabrication | P.Cwt | 362.717
4 | Filling watering ang ramming | %0Cft | 6900.67 | 0
5 | Laying white marble | P.Sft | 11933 | 0
6 | P/fixing 3/8" thick marble | P.Sft | 1740
7 | P/Laying tiles | %.Sft | 1321 | 0
8 | Glazed tile | %.Sft | 4162 | 0
9 | P/Appliing hi bond | %.Sft | 21483
10 | Providing and fixing with jute | p.Sft | 18584 | 0
11 | Preparing the surface & applying Rock | p.Sft | 17407
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 94
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.94
2 | NAME OF PROJECT | Acceleration of Additional Facilities at Culture Centre Kamal Dero (C:29.200+R:9.237)
3 | LOCATION (TALUKA/DISTRICT): | Khairpur
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 13.663 | 9.237 | 22.9
| ii) Total Release for the Current Year | 13.663 | 0 | 13.663
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 26.808 | 0 | 26.808
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
STRUCTION FOF STAGE FOR OPEN AIR AUDITORIUM WITH LAVATORY BLOCK (GROUND FLOOR)-A
1 | Laying white marble flooring | P.SFT | 7544
2 | First class deodar wood | P.SFT | 235.5
CONSTRUCTION OF LUNGARKHANO/HALL AND GUEST HOUSE WITH LAVATORY BLOCK (GROUND FLOOR)-B
1 | Laying white marble flooring | P.SFT | 1613
2 | First class deodar wood | P.SFT | 210
CONSTRUCTION OF LUNGARKHANO/HALL AND GUEST HOUSE WITH LAVATORY BLOCK (FIRST FLOOR)-B
1 | Reinforcment cement concrete work | P.CFT | 3110.92
2 | Fabrication of mild steel | P.CWT | 427.6
3 | Laying white marble flooring | P.SFT | 1510
4 | First class deodar wood | P.SFT | 92.5
CONSTRUCTION OF LUNGARKHANO/HALL AND GUEST HOUSE WITH LAVATORY BLOCK (GROUND FLOOR)-B
1 | Provinding and fixing in position teak wood door, window ventilators | P.SFT | 78
CONSTRUCTION OF LUNGARKHANO/HALL AND GUEST HOUSE WITH LAVATORY BLOCK (FIRST FLOOR)-B
1 | Provinding and fixing in position teak wood door, window ventilators | P.SFT | 86
OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 95.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.95
2 | NAME OF PROJECT | Construction of Public Library with Auditorium in Kunri District Umerkot (Revised) (C:77.155+R:17.926)
3 | LOCATION (TALUKA/DISTRICT): | Umerkot
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 22.94 | 17.926 | 40.866
| ii) Total Release for the Current Year | 22.94 | 8.963 | 31.903 | 11.47
| iii) Expenditure during the month | 0 | 1.315 | 1.315
| iv) Total Expenditure since commecement | 47.551 | 1.315 | 48.866 |  | 24.612
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
Civil Work
AUDITORIUM UNIT
1 | Excavation in foundation of building | %0CFT | 24543.69
2 | Cement concrete brick | %CFT | 1662.27
3 | Pacca brick work | %CFT | 2669.99
4 | Cement concrete plain | %CFT | 444.17
5 | Fabrication of tor steel | Per.Cwt | 146.52
6 | Reinforced cement concrete work | P.CFT | 1083.08
7 | Cement plaster 1:4 upto 12' height 3/4" thick | %SFT | 21370.94
8 | Cement plaster 1:4 upto 12' height 1/2" thick | %SFT | 21370.94
9 | First class deodar wood | P.SFT | 756
10 | Supplying & fixing in position Aluminium Channels | P.SFT | 864
11 | Iron steel grill using solid | P.SFT | 1023
12 | Laying white marble | P.SFT | 2864.25
13 | Providing and fixing 3/8" thick marble | P.SFT | 332.17
14 | Pacca brick work in ground floor | P.SFT | 6308.88
15 | Providing and Laying tiles glazed | P.SFT | 3293
16 | Filling watering and ramming earth under floor | P.CFT | 34660.55
17 | Porecelene tiles of approved design | P.SFT | 3622.94
18 | Reinforced cement concrete work including all labour and material | P.CFT | 182.25
LIBRARY UNIT
19 | Fabrication of tor steel reinforcement for cement concrete | Per.Cwt | 14.42
20 | Pacca brick work in FF | %CFT | 720.06
21 | First class deodar woodjoinery in doors and windows FF | PSFT | 96
22 | Porecelene tiles of approved design FF | PSFT | 1166
OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 96.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.96
2 | NAME OF PROJECT | Provision of Missing Allied Facilities in Larkano Arts Complex,Larkano
3 | LOCATION (TALUKA/DISTRICT): | Larkano
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 13 | 2 | 15
| ii) Total Release for the Current Year | 3.25 | 0 | 3.25
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 0 | 0 | 0
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
| 0 | 0 | 0 | 0
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 97.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.97
2 | NAME OF PROJECT | Provision of Missing Allied Facilities in Culture Complex at Umerkot.
3 | LOCATION (TALUKA/DISTRICT): | Umerkot
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 8 | 2 | 10
| ii) Total Release for the Current Year | 2 | 0 | 2
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 0 | 0 | 0
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
| 0 | 0 | 0 | 0
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 98.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.98
2 | NAME OF PROJECT | Provision of Missing Allied Facilities in Culture Complex at Nawabshah.
3 | LOCATION (TALUKA/DISTRICT): | Nawabshah
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 10 | 2.5 | 12.5
| ii) Total Release for the Current Year | 2.5 | 0 | 2.5
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 0 | 0 | 0
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
| 0 | 0 | 0 | 0
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 99.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.99
2 | NAME OF PROJECT | Provision of Missing Allied Facilities in Culture Centre at Nagarparkar.
3 | LOCATION (TALUKA/DISTRICT): | Nagarparkar
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 6.5 | 1 | 7.5
| ii) Total Release for the Current Year | 1.625 | 0 | 1.625
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 0 | 0 | 0
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
| 0 | 0 | 0 | 0
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 100.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.100
2 | NAME OF PROJECT | Provision of Missing Allied Facilities in Culture Centre at Kotri
3 | LOCATION (TALUKA/DISTRICT): | Jamshoro
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 9.25 | 2 | 11.25
| ii) Total Release for the Current Year | 2.312 | 0 | 2.312
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 0 | 0 | 0
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
| 0 | 0 | 0 | 0
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 101.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.101
2 | NAME OF PROJECT | Provision of Missing Allied Facilities in Library at Sujawal.
3 | LOCATION (TALUKA/DISTRICT): | Sujawal
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 6.25 | 1 | 7.25
| ii) Total Release for the Current Year | 1.562 | 0 | 1.562
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 0 | 0 | 0
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
| 0 | 0 | 0 | 0
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 102.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.102
2 | NAME OF PROJECT | Provision of Missing Allied Facilities in Library at K.N. Shah.
3 | LOCATION (TALUKA/DISTRICT): | Dadu
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 11.75 | 2 | 13.75
| ii) Total Release for the Current Year | 2.937 | 0 | 2.937
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 0 | 0 | 0
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
| 0 | 0 | 0 | 0
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 103.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.103
2 | NAME OF PROJECT | Provision of Missing Allied Facilities & External Development in Guest House for Artists and Writers at Hyderabad and in Majid Bhurgari Language Engineering Center at Hyderabad
3 | LOCATION (TALUKA/DISTRICT): | Hyderabad
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 9 | 1 | 10
| ii) Total Release for the Current Year | 0 | 0 | 0
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 0 | 0 | 0
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
| 0 | 0 | 0 | 0
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 104.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.104
2 | NAME OF PROJECT | Provision of Missing Allied Facilities & Constrcution of Auditorium Hall and Waiting area at Dargah Jaral Shah, Taluka Larkano District Larkano.
3 | LOCATION (TALUKA/DISTRICT): | Larkano
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 6.5 | 1 | 7.5
| ii) Total Release for the Current Year | 1.625 | 0 | 1.625
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 0 | 0 | 0
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
| 0 | 0 | 0 | 0
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 105.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.105
2 | NAME OF PROJECT | Provision of Missing Allied Facilities in Baqar Lake Resort at District Sanghar
3 | LOCATION (TALUKA/DISTRICT): | Sanghar
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 8 | 2 | 10
| ii) Total Release for the Current Year | 2 | 0 | 2
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 0 | 0 | 0
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
| 0 | 0 | 0 | 0
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 106.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.106
2 | NAME OF PROJECT | Provision of Additional Allied Facilities & External Development at Sindh Institute for Music & Performing Arts & DR. N.A Balouch Institute at Jamshoro
3 | LOCATION (TALUKA/DISTRICT): | Jamshoro
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 12.5 | 2.5 | 15
| ii) Total Release for the Current Year | 3.125 | 0 | 3.125
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 0 | 0 | 0
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
| 0 | 0 | 0 | 0
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 107.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.107
2 | NAME OF PROJECT | Provision of Additional Allied Facilities & External Development of Culture Department offices near Rumi Graveyard at Northern Bypass, Karachi
3 | LOCATION (TALUKA/DISTRICT): | Karachi
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 17.5 | 2.5 | 20
| ii) Total Release for the Current Year | 4.375 | 0 | 4.375
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 0 | 0 | 0
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
| 0 | 0 | 0 | 0
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 108.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.108
2 | NAME OF PROJECT | Provision of Additional Allied Facilities & External Development of Sub-office of Antiquities & Archaeological Museum Sukkur
3 | LOCATION (TALUKA/DISTRICT): | Sukkur
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 8.5 | 1.5 | 10
| ii) Total Release for the Current Year | 2.125 | 0 | 2.125
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 0 | 0 | 0
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
| 0 | 0 | 0 | 0
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 109.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.109
2 | NAME OF PROJECT | Protection, Preservation & Conservation of Tomb of Jam Nizamuddin in Makli Necropolis.
3 | LOCATION (TALUKA/DISTRICT): | Thatta
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 28.597 | 2 | 30.597
| ii) Total Release for the Current Year | 0 | 0 | 0
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 0 | 0 | 0
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
| 0 | 0 | 0 | 0
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 110.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.110
2 | NAME OF PROJECT | Establishment of Culture Centre at Moro.
3 | LOCATION (TALUKA/DISTRICT): | N.Feroze
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 10 | 3.25 | 13.25
| ii) Total Release for the Current Year | 2.5 | 0 | 2.5
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 0 | 0 | 0
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
| 0 | 0 | 0 | 0
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 111.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.111
2 | NAME OF PROJECT | Establishment of Muhammad Ibrahim Joyo Translation Bureau at Jamshoro
3 | LOCATION (TALUKA/DISTRICT):
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 5 | 5 | 10
| ii) Total Release for the Current Year | 0 | 0 | 0
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 0 | 0 | 0
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
| 0 | 0 | 0 | 0
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 112.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.112
2 | NAME OF PROJECT | Provision of Missing Allied Facilities in Sindhi Dictionary Board, Hyderabad
3 | LOCATION (TALUKA/DISTRICT): | Hyderabad
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 0 | 10 | 10
| ii) Total Release for the Current Year | 0 | 0 | 0
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 0 | 0 | 0
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
| 0 | 0 | 0 | 0
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 113.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.113
2 | NAME OF PROJECT | Provision of Missing Allied Facilities & Sewerage system at Tourism Sites of Thatta (Haleji lake & Shahjahan Restaurant)
3 | LOCATION (TALUKA/DISTRICT): | Thatta
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 18 | 2 | 20
| ii) Total Release for the Current Year | 4.5 | 0 | 4.5
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 0 | 0 | 0
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
| 0 | 0 | 0 | 0
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 114.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.114
2 | NAME OF PROJECT | Establishment of Model Library in Gulzar Khalil, District Umarkot.
3 | LOCATION (TALUKA/DISTRICT): | Umerkot
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 7 | 0.5 | 7.5
| ii) Total Release for the Current Year | 1.75 | 0 | 1.75
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 0 | 0 | 0
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
| 0 | 0 | 0 | 0
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 115.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.115
2 | NAME OF PROJECT | Establishment of Digitization & Conservation Laboratory for providing Physical Treatments, Testing, Cleaning and Protecting of Decaying Artifacts, i.e. Stones, Coins, Manuscripts etc.
3 | LOCATION (TALUKA/DISTRICT): | Karachi
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 22 | 2.94 | 24.94
| ii) Total Release for the Current Year | 0 | 0 | 0
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 0 | 0 | 0
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
| 0 | 0 | 0 | 0
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 116.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.116
2 | NAME OF PROJECT | Provision of Missing Allied facilities and Extension of Pakistan Institute of Tourism & Hotel Management (PITHM) Karachi
3 | LOCATION (TALUKA/DISTRICT): | Karachi
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 6 | 1.5 | 7.5
| ii) Total Release for the Current Year | 1.5 | 0 | 1.5
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 0 | 0 | 0
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
| 0 | 0 | 0 | 0
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 117.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.117
2 | NAME OF PROJECT | Missing Allied Facilities at site office Bhodesar, Nagarparkar.
3 | LOCATION (TALUKA/DISTRICT): | Tharparkar
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 6.5 | 1 | 7.5
| ii) Total Release for the Current Year | 1.625 | 0 | 1.625
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 0 | 0 | 0
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
| 0 | 0 | 0 | 0
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others

## 118.
PC-III (B) FORM
(REVISED - 2019)
GOVERNMENT OF SINDH PLANNING & DEVELOPMENT
IMPLEMENTATION OF DEVELOPMENT PROJECTS (TO BE FURNISHED BY 10TH DAY OF EACH MONTH)
1 | ADP YEAR & ADP NO. | 2019-20 ADP No.118
2 | NAME OF PROJECT | Provision of Missing Allied Facilities and Up-liftment of Old Bungalows at Keenjhar Lake, Thatta.
3 | LOCATION (TALUKA/DISTRICT): | Thatta
4 | FINANCIAL STATUS:
|  | Cap | Rev: | Total:
| i) ADP Allocations for the current Year | 8 | 2 | 10
| ii) Total Release for the Current Year | 2 | 0 | 2
| iii) Expenditure during the month | 0 | 0 | 0
| iv) Total Expenditure since commecement | 0 | 0 | 0
5 | PHYSICAL STATUS
Physical achievements during the month under report
SR. NO. | ITEMS | UNIT | QUANTITITES | REMARKS
| 0 | 0 | 0 | 0
6 | OUTPUT INDICATORS
7 | PROBLEMS/BOTTLENECKS IN PROJECTS IMPLEMENTATION
| Bank on Recruitment |  | Law & Order Situation
| Delay in Consultants Appointments |  | Management Capacity
| Lack of Coordination between Fed/Pro Govts. |  | Non Existance of PMUs
| Land Acquisition |  | Intra-Departmental Problems
| Turn Over PD/Staff |  | Procurement Problems
| Concept & Design Problems |  | Contractor's Problem
| Delay in Release of Fund |  | Others